## Schedule
Legacy Real Estate System — Delivery Schedule and Gantt
Project kickoff date | 2026-11-02 | Edit the yellow kickoff cell, the blue offset/length columns and the Status column. Everything else is calculated.
Gantt colours: red = critical path · grey = external lead time · black = milestone · other colours = phase. Durations are estimates for the developer to confirm in Phase 0.
[12 empty] | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27 |  |  |  | May 27 |  |  |  |  | Jun 27 |  |  |  | Jul 27 |  |  |  | Aug 27 |  |  |  |  | Sep 27 |  |  |  | Oct 27 |  |  |  | Nov 27 |  |  |  |  | Dec 27
Phase | Task | Epic | Type | Critical path | Start offset (days) | Length (days) | Start | End | Weeks | Status | Stories / notes | time axis 2026-11-02 to 2027-12-27
Phase 0 | Kickoff, contract and backlog review |  | Task | No | 0 | 4 | 2026-11-02 | 2026-11-06 | 1 | Not started | Agree scope, team and ways of working
Phase 0 | Close open decisions (ADRs) |  | Task | No | 0 | 11 | 2026-11-02 | 2026-11-13 | 2 | Not started | 12 business gaps + 9 technical decisions
Phase 0 | Paybill + Daraja production approval |  | External | Yes | 0 | 74 | 2026-11-02 | 2027-01-15 | 11 | Not started | Safaricom lead time; apply on day one
Phase 0 | SMS sender ID registration |  | External | No | 0 | 32 | 2026-11-02 | 2026-12-04 | 5 | Not started | Needed for receipts (LR-8.02)
Phase 0 | ODPC registration |  | External | No | 0 | 46 | 2026-11-02 | 2026-12-18 | 7 | Not started | Data controller registration (SRS §13)
Phase 0 | Monorepo, CI and k3s dev server | E13 | Task | No | 7 | 18 | 2026-11-09 | 2026-11-27 | 3 | Not started | LR-13.01, 13.17
Phase 0 | OpenAPI contract v1 and ERD | E13 | Task | No | 7 | 18 | 2026-11-09 | 2026-11-27 | 3 | Not started | LR-13.18, 13.19; data model
Phase 0 | Wireframes for Phase 1 screens |  | Task | No | 7 | 25 | 2026-11-09 | 2026-12-04 | 4 | Not started | Back office, tenant portal, caretaker view
Phase 1 | Users, roles, branch scope, audit | E1 | Task | No | 28 | 18 | 2026-11-30 | 2026-12-18 | 3 | Not started | LR-1.01 to 1.10
Phase 1 | Properties, units, landlords | E2, E3 | Task | No | 35 | 46 | 2026-12-07 | 2027-01-22 | 7 | Not started | LR-2.01 to 2.12, LR-3.01 to 3.06
Phase 1 | Tenants and tenancies | E4 | Task | No | 63 | 32 | 2027-01-04 | 2027-02-05 | 5 | Not started | LR-4.01 to 4.16 (P1)
Phase 1 | Invoicing, water billing, penalties | E5 | Task | No | 77 | 25 | 2027-01-18 | 2027-02-12 | 4 | Not started | LR-5.01 to 5.05, 5.18 to 5.20, 5.23
Phase 1 | M-Pesa C2B/STK, matching, allocation | E5 | Task | Yes | 70 | 39 | 2027-01-11 | 2027-02-19 | 6 | Not started | LR-5.06 to 5.17; queues LR-13.02 to 13.08
Phase 1 | SMS and email notifications | E8 | Task | No | 91 | 18 | 2027-02-01 | 2027-02-19 | 3 | Not started | LR-8.01 to 8.08
Phase 1 | Staging, production, DB replication | E13 | Task | No | 91 | 25 | 2027-02-01 | 2027-02-26 | 4 | Not started | LR-13.09 to 13.15
Phase 1 | Data migration and opening balances | E13 | Task | No | 105 | 18 | 2027-02-15 | 2027-03-05 | 3 | Not started | LR-13.16
Phase 1 | QA, performance, resilience, pen test |  | Task | Yes | 112 | 18 | 2027-02-22 | 2027-03-12 | 3 | Not started | SRS §18.2 test cases; LR-13.20
Phase 1 | UAT and Phase 1 sign-off |  | Task | Yes | 133 | 11 | 2027-03-15 | 2027-03-26 | 2 | Not started | Demo, UAT by agency staff, PM sign-off
Phase 1 | Phase 1 signed off |  | Milestone | Yes | 144 | 0 | 2027-03-26 | 2027-03-26 | 0 | Not started | Gate
Phase 1 | Parallel run and staff training |  | Task | Yes | 147 | 25 | 2027-03-29 | 2027-04-23 | 4 | Not started | One month against current records
Phase 1 | Rent collection go-live |  | Milestone | Yes | 175 | 0 | 2027-04-26 | 2027-04-26 | 0 | Not started | Go-live
Phase 2 | Accounting, remittances, MRI | E9 | Task | No | 147 | 32 | 2027-03-29 | 2027-04-30 | 5 | Not started | LR-9.01 to 9.08, 9.11
Phase 2 | Maintenance, caretakers, vendors | E7 | Task | No | 161 | 32 | 2027-04-12 | 2027-05-14 | 5 | Not started | LR-7.01 to 7.06, 7.10
Phase 2 | Landlord and tenant portals | E3, E4 | Task | No | 168 | 25 | 2027-04-19 | 2027-05-14 | 4 | Not started | Portal dashboards and statements
Phase 2 | Reports and dashboards | E11 | Task | No | 175 | 25 | 2027-04-26 | 2027-05-21 | 4 | Not started | LR-11.01 to 11.20 (P1)
Phase 2 | Compliance and data protection | E12 | Task | No | 182 | 18 | 2027-05-03 | 2027-05-21 | 3 | Not started | LR-12.01, 12.03 to 12.05, 12.07, 12.09, 12.10
Phase 2 | QA, UAT and sign-off |  | Task | No | 203 | 11 | 2027-05-24 | 2027-06-04 | 2 | Not started | Remittance totals match the ledger
Phase 2 | Phase 2 signed off |  | Milestone | No | 214 | 0 | 2027-06-04 | 2027-06-04 | 0 | Not started | Gate
Phase 3 | Projects, plots, sales pipeline, plans | E6 | Task | No | 217 | 32 | 2027-06-07 | 2027-07-09 | 5 | Not started | LR-6.01 to 6.09
Phase 3 | Due diligence, transfers, buyer portal | E6 | Task | No | 238 | 18 | 2027-06-28 | 2027-07-16 | 3 | Not started | LR-6.11 to 6.13
Phase 3 | QA, UAT and sign-off |  | Task | No | 259 | 11 | 2027-07-19 | 2027-07-30 | 2 | Not started | 12-month plan reminders; title tracking
Phase 3 | Phase 3 signed off |  | Milestone | No | 270 | 0 | 2027-07-30 | 2027-07-30 | 0 | Not started | Gate
Phase 4 | Public website and SEO listings | E10 | Task | No | 273 | 25 | 2027-08-02 | 2027-08-27 | 4 | Not started | LR-10.01 to 10.04
Phase 4 | Leads, viewings, match engine | E10 | Task | No | 287 | 18 | 2027-08-16 | 2027-09-03 | 3 | Not started | LR-10.06 to 10.09
Phase 4 | Extras: WhatsApp, eTIMS, Swahili, VAT |  | Task | No | 294 | 25 | 2027-08-23 | 2027-09-17 | 4 | Not started | 32 P2/P3 stories across epics
Phase 4 | Final QA, UAT and handover |  | Task | No | 315 | 11 | 2027-09-13 | 2027-09-24 | 2 | Not started | Runbooks, user guides, change log
Phase 4 | Project sign-off |  | Milestone | No | 326 | 0 | 2027-09-24 | 2027-09-24 | 0 | Not started | Gate
Phase 4 | Warranty: bug fixes |  | External | No | 329 | 88 | 2027-09-27 | 2027-12-24 | 13 | Not started | 3 months after sign-off
Note on B2: Planning assumption: kickoff Monday 2 Nov 2026. Change this date and every task date and the Gantt shift with it.

## Phases
Phases at a glance
Start and end come from the Schedule tab (external lead times excluded). P1 story counts come from the Story Counts tab.
Phase | Name | Start | End | Weeks | Epics | P1 stories | Exit gate
Phase 0 | Mobilise and set up | 2026-11-02 | 2026-12-04 | 5 | Decisions, E13 setup | 0 | Contract signed, ADRs agreed, dev server and CI running
Phase 1 | Rent collection | 2026-11-30 | 2027-04-26 | 21 | E1, E2, E3, E4, E5, E8, E13 | 88 | UAT sign-off 26 Mar, parallel run, go-live 26 Apr
Phase 2 | Accounts, maintenance, reports | 2027-03-29 | 2027-06-04 | 10 | E7, E9, E11, E12 | 39 | Landlord remittances and MRI verified against the ledger
Phase 3 | Land sales | 2027-06-07 | 2027-07-30 | 8 | E6 | 12 | 12-month buyer plan and transfer checklist pass UAT
Phase 4 | Website, CRM and extras | 2027-08-02 | 2027-09-24 | 8 | E10 + P2/P3 extras | 5 | Final sign-off and handover
Extras | P2 and P3 stories (scheduled in the Phase 4 extras window) |  |  |  |  | 32
Total | [5 empty] | 176
Key dates
Phase 1 sign-off | 2027-03-26
Rent collection go-live | 2027-04-26
Final project sign-off | 2027-09-24
Weeks from kickoff to go-live | 25
Weeks from kickoff to final sign-off | 47
Daraja approval slack before Phase 1 testing (weeks) | 5
Formulas:
Start = MINIFS(Schedule!$H7:H44,Schedule!$A7:A44,[Phase],Schedule!$D7:D44,"<>External")
End = MAXIFS(Schedule!$I7:I44,Schedule!$A7:A44,[Phase],Schedule!$D7:D44,"<>External")

## Story Counts
User stories by epic and priority
Source: Legacy Real Estate System — User Stories backlog (18 Oct 2026). P1 = first go-live, P2 = later phase, P3 = optional.
Epic | Name | P1 | P2 | P3 | Total | Phase
E1 | Access, roles and audit | 10 | 0 | 0 | 10 | Phase 1
E2 | Property and unit management | 11 | 1 | 0 | 12 | Phase 1
E3 | Landlord management | 6 | 1 | 0 | 7 | Phase 1
E4 | Tenant management and tenancies | 13 | 3 | 0 | 16 | Phase 1
E5 | Rent billing, payments and arrears | 20 | 3 | 0 | 23 | Phase 1
E6 | Land sales | 12 | 2 | 1 | 15 | Phase 3
E7 | Maintenance, caretakers and inspections | 7 | 3 | 0 | 10 | Phase 2
E8 | Communications | 8 | 2 | 0 | 10 | Phase 1
E9 | Accounting, remittances and tax | 9 | 4 | 0 | 13 | Phase 2
E10 | Public website and CRM | 5 | 4 | 1 | 10 | Phase 4
E11 | Reports and dashboards | 16 | 4 | 0 | 20 | Phase 2
E12 | Compliance and data protection | 7 | 3 | 0 | 10 | Phase 2
E13 | Platform, infrastructure, non-functional | 20 | 0 | 0 | 20 | Phase 1
Total |  | 144 | 30 | 2 | 176
Largest epic | Rent billing, payments and arrears
Share of P1 stories in Phase 1 | 61.11%

## Analysis
Analysis, critical path, assumptions and risks
Critical path
1 | Paybill and Daraja production approval
2 | M-Pesa matching and allocation
3 | Phase 1 QA, performance and resilience tests
4 | UAT and sign-off
5 | One-month parallel run
6 | Rent collection go-live
Findings
• | Payments are the heaviest epic: Epic 5 has 23 stories and touches billing, accounting, notifications and the queues.
• | Platform work comes first: queues, idempotent callbacks, replication and Kubernetes (Epic 13, 20 stories) must be ready before payments can be tested.
• | Three outside lead times start on day one: Paybill/Daraja approval, SMS sender ID and ODPC registration (SRS §18.3).
• | 21 decisions are still open (12 business gaps + 9 technical decisions); Phase 0 sets aside two weeks to close them.
• | The website comes last because the SRS ranks it below rent collection; Epic 10 can move into Phase 2 with about 4 more weeks of effort.
Planning assumptions
• | Kickoff Monday 2 November 2026 (editable on the Schedule tab).
• | Team: one lead full-stack developer, one frontend developer, QA and a project manager. A single developer roughly doubles the build durations.
• | Light work from 21 December to 1 January.
• | Each phase ends with a demo, UAT by agency staff and PM sign-off (SRS §18).
• | Go-live follows the SRS: data migration, one-month parallel run, staff training, switch-over.
• | Warranty: 3 months of bug fixes after final sign-off.
Schedule risks
| Risk | Impact | Mitigation
| Daraja approval takes longer than 11 weeks | Go-live slips | Apply on day one; build against the sandbox; about 5 weeks of slack
| Open decisions not closed in Phase 0 | Schema rework mid-build | Two-week decision window; ADRs signed off before modules start
| Opening balances do not reconcile | Wrong arrears from day one | Import validation per row; one-month parallel run
| Team smaller than assumed | Build bars roughly double | Re-estimate in Phase 0; protect the rent-collection scope
| December holiday slowdown | Phase 1 build compressed | Shaded on the plan; avoid gates in the holiday weeks